## Sheet1
Date | Project | Discription
2025-04-01 | Little Money Website | Worked on the PL and BL form validations part and worked on the client changes on Frontend part of home page ,our partners,services page.
2025-04-02 | Little Money Website | Worked on criteria and cutoff according to the client requirement and modified the Frontend part that is Our patners ,referral code section,social links
2025-04-03 | Little Money Website | Started with little money website backend,created folder structure of the complete backend and modified some UI changes said by Client
2025-04-04 | Little Money Website | Worked on the referral code which I had implemented according to how credit links had done.
2025-04-07 | Little Money Website | Created the API's to send OTP via phone number using edumarc sms API.
2025-04-08 | Little Money Website | Worked on Kods Website,Business Loans Form to conditionally render all the fields,performed UI modifications
2025-04-09 | Little Money Website | Attended the client meeting,Worked on the business loans form according to client requirement,worked with sibarchan to for making the website responsive on medium screen sizes.
2025-04-10 | Little Money Website | Worked on the Frontend changes said by client on the about us page,Added the updated API keys for getting the response based on the loannet API's
2025-04-11 | Little Money Website | Worked on resend OTP functionality ,implemented personal loan eligibility check API.
2025-04-14 | Little Money Website | Started working on lead creation API, Offers API,summary API and started working on client feedbacks
2025-04-15 | Little Money Website | Worked on the flow of how users gets redirected to offers page when lead is provided and completed the refferal code section,worked on modifications said by client
2025-04-16 | Little Money Website | Added SEO configuration to the frontend,Worked on schema of offers and applied customers to save the count of customers who applied for each offer
2025-04-17 | Little Money Website | Worked on the flow of customer gets redirected to offers page after 30 days using cron npm package, Added QR code on the offers page,Added the offers card and modified the UI
2025-04-21 | Little Money Website | Implemented Auto Logout functionality using session storage,modified the PAN validation as client said,started working on Edit profile section
2025-04-22 | Little Money Website | Completed the Edit Profile section Worked on URL part ,Added the validations on name field such that they wont take spaces according to the client's requirement
2025-04-23 | Little Money Website | Completed the Business Loan schema,Completed the dedupe API and Lead Api of Business loans
2025-04-24 | Little Money Website | Removed some fields from Business loans form according to the client requirement modified the API's of business loans section
2025-04-25 | Little Money Website | Worked on the Edit profile section of Business loan ,performed client changes on UI
2025-04-28 | Little Money Website | created the offers API,summary API for business loans section and connected it to fronted
2025-04-29 | Little Money Website | Added all the privacy policy and terms and conditions on the form pages,modified the UI according to clients requirement
2025-04-30 | Little Money Website | Worked on the Employement status part of business loans section as client's requirement and modified all the API's related to that form that are lead API,Offers API,Summary API.
2025-05-01 | Little Money Website | Performed the client's modifications on the frontend
2025-05-02 | Little Money Admin Panel | Started working on Little Money Admin panel Backend,Created the folder structure,created Email and OTP verification API,Completed the 2 factor authentication of admin
2025-05-05 | Little Money Admin Panel | Worked on the Loans section of Admin panel,created the schema for all-details by referencing the personal loan,business loan,login count ,applied customers schemas.
2025-05-06 | Little Money Admin Panel | Connected the summaries API for displaying the total offers of each lead and fetching the summaries of each lead,added filter functionality based on type of loan and date range by creating the API's for both.
2025-05-07 | Little Money Admin Panel | Implemented the search functionality on the Admin page based on lead and phone number,created API's for both,added the view offers section for the admin to see offers of each lead
2025-05-08 | Little Money Admin Panel | Worked on the dashboard section of admin panel,Added the total loans count on dashboard,modified the fetching of data from cosmos db.
Backend of merchant and store is pending